## Sheet1
Assumptions:
Transaction data is already in the database
Req # | Details | Estimate | Tasks
1 | Import todays datafile of payment data into the transaction system | 1 | Load payment data to transaction database from network location
|  | 0.5 | > create upload file process screen
|  | 0.1 | > read/parse file
|  | 0.2 | > insert payment data to DB
> run reconciliation (see req 2)
2 | Check for missing transaction amount in todays file | 0.5 | Create Reconcilliation process
|  | 0.5 | > compare daily file(s) data to transaction data
> check for blank / missing
> check for mismatch on payment amount
> mark record if mismatch found and mark status code to ERROR or some other value
> Load failed reconciliation record to "Mismatch table" with status reason field of what the error is
3 | User selects todays date and reconcile | 0.5 | Show reconciliation by date selected
> Screen for user to select a date option filter for triggering reconciliation
> trigger reconciliation process (see req 2)
> Display status of reconciliation (Good or things to fix)
4 | Display status of reconciliation | 0.5 | Display status of reconciliation
> All in balance, go to req #8
> user prompt to make updates, or quit.
> Quit, notify files are not in balance - just go back to home page or leave app (TBD)
> Update/correct payment record - Go to Req 5
5 | Allow user to update payment information in a single payment transaction | 1 | Work records in Needs Attention queue
|  | 0.2 | > Display record needing updates based on status codes
|  | 0.5 | > User can select record to edit & display the payment & transaction data records for comparison for updating
|  | 0.1 | > User can update transaction amount
|  | 0.1 | > User can change lender name from drop down list if desired
|  | 0.1 | > User adds 1 of 5 reason codes from drop down
|  | 0.1 | > User is asked to confirm changes and send for approval by supervisor
>>> no, continue editing
6 | Create summary of the changed payment transaction detail and put in a queue for supervisor approval |  | Create supervisor review screen
> Displays data from original payment data file, transaction data file and the updated mismatch table > Include user name, reason text and date/time changed
7 | Supervisor reviews transactions that are in Awaiting Approval & update status |  | review transactions & approve or reject
8 | Acknowledge